## 2020-21 Programme
WARD | ROAD NAME | DISTRICT | WORKS | TREATMENT | WORK STAGE
ANSTON & WOODSETTS | LINDRICK ROAD | WOODSETTS | INSTALL NEW HIGHWAY DRAINAGE SYSTEM, GULLIES AND SOAKAWAY | Repair Highway Drain | COMPLETE
ANSTON & WOODSETTS | WOODSETTS ROAD | NORTH ANSTON | INSTALL GULLIES AND CHANNEL GRATING | Gully Installation | OCT-DEC
BRINSWORTH & CATCLIFFE | CHALLINER MEWS | CATCLIFFE | REINSTATE DITCH | Cleansing / Silt Removal | COMPLETE
DINNINGTON | QUEEN STREET | DINNINGTON | INSTALL NEW GULLIES AND CONNECTION | Gully Installation | COMPLETE
DINNINGTON | NEW ROAD | FIRBECK | REPAIR HIGHWAY DRAIN | Repair Highway Drain | OCT-DEC
DINNINGTON | OUTGANG LANE | DINNINGTON | REPAIR CULVERTED WATERCOURSE | Culvert Repair | COMPLETE
DINNINGTON | NEW ROAD | FIRBECK | INSTALL ADDITION GULLIES AND CONNECTIONS | Gully Installation | COMPLETE
DINNINGTON | CONSTABLE LANE | DINNINGTON | INSTALL CHANNEL GRATES | Gully Installation | COMPLETE
DINNINGTON | OUTGANG LANE | DINNINGTON | REPAIR HIGHWAY DRAIN | Repair Highway Drain | COMPLETE
HELLABY | BAWTRY ROAD | BRAMLEY | REPAIR HIGHWAY DRAIN | Repair Highway Drain | COMPLETE
HOLDERNESS | WEST LANE | AUGHTON | REPAIR HIGHWAY DRAIN | Repair Highway Drain | COMPLETE
ROTHER VALE | TOAD LANE | BRAMPTON-EN-LE-MORTHERN | REPAIR HIGHWAY CULVERT | Culvert Repair | COMPLETE
ROTHERHAM EAST | PARK ROAD | EAST DENE | INSTALL ADDITION HIGHWAY GULLIES | Gully Installation | COMPLETE
ROTHERHAM WEST | CAVENDISH ROAD | HOLMES | GULLY REPLACEMENT | Gully Installation | OCT-DEC
ROTHERHAM WEST | JOSEPHINE ROAD | HOLMES | GULLY REPLACEMENT | Gully Installation | OCT-DEC
ROTHERHAM WEST | HOLMES LANE | HOLMES | GULLY REPLACEMENT | Gully Installation | COMPLETE
ROTHERHAM WEST | BELMONT STREET | HOLMES | GULLY REPLACEMENT | Gully Installation | COMPLETE
SILVERWOOD | CARR LANE | THRYBERGH | CLEANSE / REMOVE SILT FROM HIGHWAY DITCH | Repair Highway Drain | COMPLETE
SILVERWOOD | CHURCH LANE | RAVENFIELD | REPAIR CULVERT | Culvert Repair | JULY-SEPT
SILVERWOOD | GLASSHOUSE LANE | KILNHURST | CLEANSE / REMOVE SILT FROM HIGHWAY DITCH | Cleansing / Silt Removal | COMPLETE
SITWELL | MORTHEN HALL LANE | MORTHEN | REPAIR CULVERT UNDER HIGHWAY | Culvert Repair | COMPLETE
VALLEY | HOLLINGS LANE | THRYBERGH | REPAIR HIGHWAY DRAIN | Repair Highway Drain | COMPLETE
VALLEY | FAR DALTON LANE | DALTON | INSTALL FILTER DRAIN ALONG SIDE OF HIGHWAY | Installation of Land Drain | COMPLETE
WATH | DEARNE ROAD | WATH-UPON-DEARNE | CLEANSING / REMOVE SILT FROM HIGHWAY DITCH | Cleansing / Silt Removal | OCT-DEC
WATH | WARREN VALE ROAD | SWINTON | INSTALL ADDITIONAL GULLIES | Gully Installation | OCT-DEC
WICKERSLEY | PARK GROVE | BRAMLEY | INSTALL NEW GULLIES | Gully Installation | COMPLETE
WINGFIELD | CAR HILL | BARBOT HALL | REINSTATE FILTER DRAIN AND REPAIR HIGHWAY DRAIN | Repair Highway Drain | COMPLETE
WINGFIELD | POTTER HILL | GREASBROUGH | INSTALL LAND DRAIN | Installation of Land Drain | COMPLETE